## ger garage
ger garage
Manage any type of project. Assign owners, set timelines and keep track of where your project stands.
last month
Name | Subtasks | Status | Timeline - Start | Timeline - End
Definition and Planning | Initial meeting and requirement definition, Site structure creation and page planning, Interface design and initial prototyping | Done | 2023-06-01 | 2023-06-08
Subitems | Name | Owner | Status | Due Date
| Initial meeting and requirement definition |  | Done | 2023-03-07
| Site structure creation and page planning |  | Done
| Interface design and initial prototyping |  | Done
Base Development | Development environment setup and technology selection, Database architecture creation, HTML and CSS structure development | Done | 2023-06-09 | 2023-06-19
Subitems | Name | Owner | Status | Due Date
| Development environment setup and technology selection |  | Done
| Database architecture creation |  | Done
| HTML and CSS structure development |  | Done
Functionality Development | User registration and authentication implementation, Integration of contact forms and subscription, Image gallery development | Done | 2023-06-28 | 2023-06-28
Subitems | Name | Owner | Status | Due Date
| User registration and authentication implementation |  | Done
| Integration of contact forms and subscription |  | Done
| Image gallery development |  | Done
Optimization and Testing | Performance optimization and load time improvement, Compatibility testing across different browsers, Functionality testing on various devices | Done | 2023-06-29 | 2023-07-13
Subitems | Name | Owner | Status | Due Date
| Performance optimization and load time improvement |  | Done
| Compatibility testing across different browsers |  | Done
| Functionality testing on various devices |  | Done
Content and Polishing | ext and multimedia content creation and editing, Final design and style adjustments, General page review and minor error corrections | Done | 2023-07-14 | 2023-07-25
Subitems | Name | Owner | Status | Due Date
ext and multimedia content creation and editing
Final design and style adjustments
General page review and minor error corrections
Launch and Delivery | Hosting infrastructure preparation, Website publishing and launch, Final project delivery and documentation | Done | 2023-07-26 | 2023-08-10
Subitems | Name | Owner | Status | Due Date
| Hosting infrastructure preparation |  | Done
| Website publishing and launch |  | Working on it
| Final project delivery and documentation |  | Stuck
|  |  | 2023-06-01 | 2023-08-10
Next month
Name | Subtasks | Status | Timeline - Start | Timeline - End